## Sheet1
Issues | Probability | Severity | Mitigation
Computer Crashes | Low | Severe | Frequently push code to GitHub.
Wi-Fi goes down | High | Inconvenience | Go to a nearby coffee shop, Pitt, or Duquesne.
Project gets to big to fit on computer | Probable | Inconvenience - Severe (depending on how big) | Depending on how much the size is, delete unused data/programs or buy a hard drive.
Poor planning/missed timeline estimations | Low | Severe | Create Gantt Chart to plan different/alternative plans.
Requirements change by customer | High | Severe | Make train data, and modules as generic as possible.
Snow Storms and other natural disasters prevent from meeting | Probable | Inconvenience | Video meeting, meet a different day, communicate on Slack,
Group member becomes sick | High | Inconvenience - Severe | If task isn't too big, have another group member take it on, make sure person catches up
People miss meetings | High | Inconvenience | Fill them in on Slack, or though some other way (meeting, 1-1, etc..)
Integration problems | Low | Inconvenience | Test the code frequently to make sure it passes tests.
Someone pushes to master without passing tests | Probable | Inconvenience - Severe (depending on code) | Go over proper use of git
Requirements misunderstood | Probable | Inconvenience - Severe | Modularize code to make changes easy
Units aren’t compatible with other modules | Low | Inconvenience | Make sure everyone is on the same page about units
GitHub shuts down | Low | Severe | Back up repo to local drive, move over to GitLab
Group: Low-Comotivation
Christen Reinbeck, Max Reno, Zach Scheider, Demetri, Andrew Lendacky, Michael Ghaben